## Sheet1
Activity ID | Activity Name | WBS Code | WBS Level | Discipline | Planned Start | Planned Finish | Planned Duration | Actual Progress % | Contractor
EW-L1-001 | East-West Gas Pipeline Sector 4 EPC | 1 | L1 | General | 2026-08-03 | 2027-01-30 | 180 | 42 | Larsen & Petro Engineering JV
CIV-L2-001 | Civil & Structural Works Package | 1.1 | L2 | Civil | 2026-08-03 | 2026-12-01 | 120 | 68 | Larsen & Petro Engineering JV
PIP-L2-001 | Mainline & Station Piping Package | 1.2 | L2 | Piping | 2026-08-18 | 2027-01-15 | 150 | 40 | Larsen & Petro Engineering JV
MEC-L2-001 | Static & Rotary Equipment Package | 1.3 | L2 | Mechanical | 2026-09-02 | 2026-12-21 | 110 | 25 | Larsen & Petro Engineering JV
ELE-L2-001 | Power Distribution & Substation Package | 1.4 | L2 | Electrical | 2026-08-28 | 2026-12-06 | 100 | 32 | Larsen & Petro Engineering JV
HSE-L2-001 | Health, Safety & Environmental Assurance | 1.5 | L2 | HSE | 2026-08-03 | 2027-01-30 | 180 | 80 | Larsen & Petro Engineering JV
CIV-L5-010 | Route Grading & ROW Trench Excavation Km 12-28 | 1.1.1.1.1 | L5 | Civil | 2026-08-03 | 2026-09-12 | 40 | 100 | Larsen & Petro Engineering JV
CIV-L5-012 | Reinforced Concrete Pile Cap & Foundation for Compressor Skid | 1.1.1.1.2 | L5 | Civil | 2026-08-13 | 2026-09-12 | 30 | 92 | Larsen & Petro Engineering JV
CIV-L6-015 | Valve Pit #4 Concrete Pouring, Shuttering & Curing | 1.1.1.1.3.1 | L6 | Civil | 2026-09-07 | 2026-10-02 | 25 | 75 | Larsen & Petro Engineering JV
CIV-L6-018 | Anchor Block Cast-in-Place for 24" River Crossing | 1.1.1.1.3.2 | L6 | Civil | 2026-09-12 | 2026-10-02 | 20 | 30 | Larsen & Petro Engineering JV
PIP-L5-020 | Mainline 24" API 5L X70 Pipe Stringing & Cold Bending | 1.2.1.1.1 | L5 | Piping | 2026-08-18 | 2026-09-22 | 35 | 90 | Larsen & Petro Engineering JV
PIP-L5-022 | Automatic Orbital Trench Welding & Ultrasonic NDT Inspection | 1.2.1.1.2 | L5 | Piping | 2026-08-28 | 2026-10-12 | 45 | 50 | Larsen & Petro Engineering JV
PIP-L6-024 | Erect Line 24"-XX Compressor Station Tie-in Spools | 1.2.1.1.3.1 | L6 | Piping | 2026-08-23 | 2026-10-02 | 40 | 45 | Larsen & Petro Engineering JV
PIP-L6-026 | 18" Bypass Loop Header Fabrication & Hydro-Flange Assembly | 1.2.1.1.3.2 | L6 | Piping | 2026-09-07 | 2026-10-07 | 30 | 20 | Larsen & Petro Engineering JV
PIP-L6-028 | Hydrostatic Pressure Testing Sector 4 (Section A 120 Bar) | 1.2.1.1.4.1 | L6 | Piping | 2026-10-07 | 2026-10-27 | 20 | 0 | Larsen & Petro Engineering JV
MEC-L5-031 | Centrifugal Gas Compressor Unit 01 Skid Rigging & Positioning | 1.3.1.1.1 | L5 | Mechanical | 2026-09-02 | 2026-09-27 | 25 | 60 | Larsen & Petro Engineering JV
MEC-L6-035 | Turbine Lube Oil System Stainless Piping & High-Velocity Flush | 1.3.1.1.2.1 | L6 | Mechanical | 2026-09-09 | 2026-10-01 | 22 | 35 | Larsen & Petro Engineering JV
MEC-L6-038 | Suction Scrubber & Knock-Out Drum Internal Demister Installation | 1.3.1.1.2.2 | L6 | Mechanical | 2026-09-15 | 2026-10-03 | 18 | 10 | Larsen & Petro Engineering JV
ELE-L5-041 | High Voltage 33kV Armored Cable Trenching & Sand Bedding | 1.4.1.1.1 | L5 | Electrical | 2026-08-28 | 2026-09-27 | 30 | 80 | Larsen & Petro Engineering JV
ELE-L6-044 | Transformer Substation T-102 High-Pot Testing & Panel Termination | 1.4.1.1.2.1 | L6 | Electrical | 2026-09-07 | 2026-10-02 | 25 | 40 | Larsen & Petro Engineering JV
ELE-L6-048 | Emergency Gas Detection & Optical Flame Sensor Loop Checking | 1.4.1.1.3.1 | L6 | Electrical | 2026-09-22 | 2026-10-12 | 20 | 0 | Larsen & Petro Engineering JV
HSE-L5-051 | Hot Work Containment Barriers & Gas Sniffing Station Setup | 1.5.1.1.1 | L5 | HSE | 2026-08-08 | 2026-09-07 | 30 | 100 | Larsen & Petro Engineering JV
HSE-L6-054 | Emergency Evacuation Sirens & High-Pressure Blast Wall Inspection | 1.5.1.1.2.1 | L6 | HSE | 2026-09-02 | 2026-09-22 | 20 | 70 | Larsen & Petro Engineering JV